## About
Illustrative example — synthetic
Product | Mobily Transformation Hub
Output | Registers
Transformation | ROAMING — International Roaming Transformation
Subject | ROAMING — International Roaming Transformation
Period
As of | 2026-10-18 06:13 (Asia/Riyadh)
Snapshot ID | 01a14d00-2063-747e-bada-9fc261486df2
Issue | Draft — not an issued report
Methodology version | playbook v1
Approval state of the sources (recorded, not an approval) | Not applicable
Filters
No filters
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Title
Illustrative example — synthetic
Title
Code | Type | Description | Impact | Probability | Owner | Due date | Mitigation | Status
DEP-01 | Dependency | Digital activation needs the partner usage feed from Partner optimization (synthetic). | Medium | n/a | roaming.user.wl (synthetic) | 2026-10-01 | Unknown | Open
R-01 | Risk | Partner settlement data arrives late, so cost/MB is reported stale (synthetic). | Medium | High | roaming.user.kds (synthetic) | 2026-09-21 | Agree a settlement data cut-off with the top partners (synthetic). | Open
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Legend
Illustrative example — synthetic
Validation labels
Validated | The value is validated by its owner process.
Provisional | The value is provisional: pending validation or approval; it is shown and counted.
Unknown | No value is available; the cell is empty and is never shown as 0.
Stale | The value is out of date; no current number is shown.
n/a | The value does not apply to this record.
Totals marked as formulas are computed by the spreadsheet from the rows above; text never becomes a formula.
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.