## Slide 1
Illustrative example — synthetic
Mobily Transformation Hub
Wave roadmap
Product | Mobily Transformation Hub
Output | Wave roadmap
Transformation | ROAMING — International Roaming Transformation
Subject | ROAMING — International Roaming Transformation
Period | 
As of | 2026-10-23 08:43 (Asia/Riyadh)
Snapshot ID | 01a16748-ee9e-775c-8e5f-3cedb4730e17
Issue | Draft — not an issued report
Methodology version | playbook v1
Approval state of the sources (recorded, not an approval) | Not applicable
Draft — not an issued report
Slide 1 of 7

## Slide 2
Illustrative example — synthetic
Waves
Code | Name (English) | Name (Arabic) | Purpose (English) | Purpose (Arabic) | Planned start | Planned end | Owner | Status
wave_0 n/a | Wave 0 — Mobilize n/a | الموجة 0 — التعبئة n/a | Baseline, governance, design decisions n/a | الخط الأساسي، والحوكمة، وقرارات التصميم n/a | Unknown | Unknown | Unknown | Active n/a
wave_1 n/a | Wave 1 — Prove n/a | الموجة 1 — الإثبات n/a | Quick wins / pilots / de-risking n/a | مكاسب سريعة / تجارب / تقليل المخاطر n/a | Unknown | Unknown | Unknown | Active n/a
wave_2 n/a | Wave 2 — Scale n/a | الموجة 2 — التوسّع n/a | Scale validated changes n/a | توسيع التغييرات المُتحقق منها n/a | Unknown | Unknown | Unknown | Active n/a
wave_3 n/a | Wave 3 — Embed n/a | الموجة 3 — الترسيخ n/a | BAU integration / optimization n/a | الدمج في العمليات الاعتيادية / التحسين n/a | Unknown | Unknown | Unknown | Active n/a
Draft — not an issued report
Slide 2 of 7

## Slide 3
Illustrative example — synthetic
Initiatives
Code | Name | Wave | Executive owner | Workstream lead | Objective | Planned start | Planned end | Status
INI-01 n/a | Pass redesign + digital activation n/a | wave_1 n/a | roaming.user.sp (synthetic) n/a | roaming.user.wl (synthetic) n/a | Attach rate / activation -> Revenue uplift (B0147, synthetic illustrative example). n/a | 2026-07-03 n/a | 2026-12-30 n/a | Launched n/a
INI-02 n/a | Proactive comms + QoS monitoring n/a | wave_1 n/a | roaming.user.sp (synthetic) n/a | roaming.user.wl (synthetic) n/a | Complaint rate -> CX + care cost (B0147, synthetic illustrative example). n/a | 2026-07-03 n/a | 2026-12-30 n/a | Launched n/a
INI-03 n/a | Partner optimization n/a | wave_1 n/a | roaming.user.sp (synthetic) n/a | roaming.user.wl (synthetic) n/a | Cost/MB, margin -> Margin improvement (B0147, synthetic illustrative example). n/a | 2026-07-03 n/a | 2026-12-30 n/a | Launched n/a
Draft — not an issued report
Slide 3 of 7

## Slide 4
Illustrative example — synthetic
Milestones
Initiative | Title | Wave | Approved date | Forecast date | Actual date | Owner | Status
INI-01 n/a | Roaming pass architecture redesigned (synthetic) n/a | wave_1 n/a | 2026-09-30 n/a | 2026-09-30 n/a | n/a | roaming.user.wl (synthetic) n/a | Planned n/a
INI-01 n/a | One-tap digital activation live in the app (synthetic) n/a | wave_1 n/a | 2026-11-30 n/a | 2026-11-30 n/a | n/a | roaming.user.wl (synthetic) n/a | Planned n/a
INI-02 n/a | QoS monitoring live for the top roaming destinations (synthetic) n/a | wave_1 n/a | 2026-10-15 n/a | 2026-10-15 n/a | n/a | roaming.user.wl (synthetic) n/a | Planned n/a
INI-02 n/a | Proactive travel notifications live (synthetic) n/a | wave_1 n/a | 2026-12-15 n/a | 2026-12-15 n/a | n/a | roaming.user.wl (synthetic) n/a | Planned n/a
INI-03 n/a | Partner cost analytics baseline delivered (synthetic) n/a | wave_1 n/a | 2026-09-15 n/a | 2026-09-15 n/a | n/a | roaming.user.wl (synthetic) n/a | Planned n/a
INI-03 n/a | Partner usage feed live for digital activation (synthetic) n/a | wave_1 n/a | 2026-09-28 n/a | 2026-09-28 n/a | n/a | roaming.user.wl (synthetic) n/a | Planned n/a
Draft — not an issued report
Slide 4 of 7

## Slide 5
Illustrative example — synthetic
Dependencies
Code | From initiative | To initiative | Type | Description | Needed by | Owner | Status
DEP-01 n/a | INI-03 n/a | INI-01 n/a | Data n/a | Digital activation needs the partner usage feed from Partner optimization (synthetic). n/a | 2026-10-01 n/a | roaming.user.wl (synthetic) n/a | Open n/a
Draft — not an issued report
Slide 5 of 7

## Slide 6
Illustrative example — synthetic
Validation labels
Validated | The value is validated by its owner process.
Provisional | The value is provisional: pending validation or approval; it is shown and counted.
Unknown | No value is available; the cell is empty and is never shown as 0.
Stale | The value is out of date; no current number is shown.
n/a | The value does not apply to this record.
 | Totals marked as formulas are computed by the spreadsheet from the rows above; text never becomes a formula.
Draft — not an issued report
Slide 6 of 7

## Slide 7
Illustrative example — synthetic
About this file
Fonts: this presentation names IBM Plex Sans Arabic and IBM Plex Sans (SIL Open Font License 1.1) and does not embed them; a viewer without them shows a substitute font.
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.
Draft — not an issued report
Slide 7 of 7