## Slide 1
Illustrative example — synthetic
Mobily Transformation Hub
Executive pack
Product | Mobily Transformation Hub
Output | Executive pack
Transformation | ROAMING — International Roaming Transformation
Subject | ROAMING — International Roaming Transformation
Period | 2026-09 (2026-09-01 – 2026-09-30)
As of | 2026-10-18 17:35 (Asia/Riyadh)
Snapshot ID | 01a14f70-bc65-737d-82dc-30c626796aa7
Issue | Draft — not an issued report
Methodology version | playbook v1
Approval state of the sources (recorded, not an approval) | Not applicable
Draft — not an issued report
Slide 1 of 8

## Slide 2
Illustrative example — synthetic
Owner update
Label | Value
Subject | ROAMING International Roaming Transformation n/a
Update | No update submitted n/a
Draft — not an issued report
Slide 2 of 8

## Slide 3
Illustrative example — synthetic
Current metrics
Label | Value
Outcomes | Unknown
Value | Red n/a
Portfolio | Not applicable n/a
Dependencies | Green n/a
Decisions | Green n/a
People & adoption | Unknown
Outcome KPIs | 3 n/a
Planned value (profit and cash) | SAR 120,000 n/a
Forecast value (profit and cash) | SAR 0 Provisional
Draft — not an issued report
Slide 3 of 8

## Slide 4
Illustrative example — synthetic
Current metrics (continued)
Label | Value
Submitted value (profit and cash) | SAR 0 Provisional
Validated value (profit and cash) | SAR 0
Value gap (profit and cash) | 1 n/a
Planned revenue uplift (top line; not in profit and cash) | SAR 396,000 n/a
Forecast revenue uplift (top line; not in profit and cash) | SAR 148,500 Provisional
Submitted revenue uplift (top line; not in profit and cash) | SAR 0 Provisional
Validated revenue uplift (top line; not in profit and cash) | SAR 0
Value gap (top line; not in profit and cash) | 1 n/a
Planned avoided cost (non-cash; not in profit and cash) | SAR 79,200 n/a
Draft — not an issued report
Slide 4 of 8

## Slide 5
Illustrative example — synthetic
Current metrics (continued)
Label | Value
Forecast avoided cost (non-cash; not in profit and cash) | SAR 0 Provisional
Submitted avoided cost (non-cash; not in profit and cash) | SAR 0 Provisional
Validated avoided cost (non-cash; not in profit and cash) | SAR 0
Value gap (non-cash; not in profit and cash) | 1 n/a
Investment | SAR 4,830,000 n/a
Top initiatives | 0 n/a
Open dependencies | 0 n/a
Open decisions | 0 n/a
Overdue decisions | 0 n/a
Draft — not an issued report
Slide 5 of 8

## Slide 6
Illustrative example — synthetic
Current metrics (continued)
Label | Value
Adoption indicators | 0 n/a
Open risks | 1 n/a
Open assumptions | 0 n/a
Open issues | 0 n/a
Open dependencies (RAID) | 1 n/a
Draft — not an issued report
Slide 6 of 8

## Slide 7
Illustrative example — synthetic
Validation labels
Validated | The value is validated by its owner process.
Provisional | The value is provisional: pending validation or approval; it is shown and counted.
Unknown | No value is available; the cell is empty and is never shown as 0.
Stale | The value is out of date; no current number is shown.
n/a | The value does not apply to this record.
 | Totals marked as formulas are computed by the spreadsheet from the rows above; text never becomes a formula.
Draft — not an issued report
Slide 7 of 8

## Slide 8
Illustrative example — synthetic
About this file
Fonts: this presentation names IBM Plex Sans Arabic and IBM Plex Sans (SIL Open Font License 1.1) and does not embed them; a viewer without them shows a substitute font.
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.
Draft — not an issued report
Slide 8 of 8