## About
Illustrative example — synthetic
Product | Mobily Transformation Hub
Output | Registers
Transformation | ROAMING — International Roaming Transformation
Subject | ROAMING — International Roaming Transformation
Period
As of | 2026-10-18 17:35 (Asia/Riyadh)
Snapshot ID | 01a14f70-c024-75ac-85b2-426dd6a38ef2
Issue | Draft — not an issued report
Methodology version | playbook v1
Approval state of the sources (recorded, not an approval) | Not applicable
Filters
No filters
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Title
Illustrative example — synthetic
Title
Code | Title | Benefit type | Value class | Baseline | Baseline — status | Baseline unit | Target | Target — status | Planned value | Planned value — status | Realized value (validated) | Realized value (validated) — status | Realized value (sustained) | Realized value (sustained) — status | Value pending Finance validation | Value pending Finance validation — status | Lines pending validation | Owner | Status | Lifecycle step | Counting
B01 | Revenue uplift | Revenue | Revenue uplift | 0.18 | Validated | fraction | 0.24 | n/a | 7128000 | n/a | 222750 | Validated | 0 | n/a | 99000 | Provisional | 1 | roaming.user.bo (synthetic) | Unknown | Measure | Counted
B02 | CX + care cost | Cost | Avoided cost | 0.035 | Provisional | fraction | 0.025 | n/a | 1584000 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | roaming.user.bo (synthetic) | Unknown | Enable | Counted
B03 | Margin improvement | Revenue | Margin uplift | 0.012 | Validated | SAR per MB | 0.01 | n/a | 1920000 | n/a | 80000 | Validated | 0 | n/a | 0 | n/a | 0 | roaming.user.bo (synthetic) | Unknown | Measure | Counted
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Revenue uplift
Illustrative example — synthetic
Revenue uplift
Code | Title | Realized value (validated) | Realized value (validated) — status | Realized value (sustained) | Realized value (sustained) — status | Value pending Finance validation | Value pending Finance validation — status
B01 | Revenue uplift | 222750 | Validated | 0 | n/a | 99000 | Provisional
Total |  | 222750 | Validated | 0 | n/a | 99000 | Provisional
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Margin uplift
Illustrative example — synthetic
Margin uplift
Code | Title | Realized value (validated) | Realized value (validated) — status | Realized value (sustained) | Realized value (sustained) — status | Value pending Finance validation | Value pending Finance validation — status
B03 | Margin improvement | 80000 | Validated | 0 | n/a | 0 | n/a
Total |  | 80000 | Validated | 0 | n/a | 0 | n/a
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Avoided cost
Illustrative example — synthetic
Avoided cost
Code | Title | Realized value (validated) | Realized value (validated) — status | Realized value (sustained) | Realized value (sustained) — status | Value pending Finance validation | Value pending Finance validation — status
B02 | CX + care cost | 0 | n/a | 0 | n/a | 0 | n/a
Total |  | 0 | n/a | 0 | n/a | 0 | n/a
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Legend
Illustrative example — synthetic
Validation labels
Validated | The value is validated by its owner process.
Provisional | The value is provisional: pending validation or approval; it is shown and counted.
Unknown | No value is available; the cell is empty and is never shown as 0.
Stale | The value is out of date; no current number is shown.
n/a | The value does not apply to this record.
Totals marked as formulas are computed by the spreadsheet from the rows above; text never becomes a formula.
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.