## Slide 1
Illustrative example — synthetic
Mobily Transformation Hub
Gate pack
Product | Mobily Transformation Hub
Output | Gate pack
Transformation | ROAMING — International Roaming Transformation
Subject | G1 — ROAMING G1
Period | 
As of | 2026-10-21 22:02 (Asia/Riyadh)
Snapshot ID | 01a15fd7-fdf5-76c1-bb39-559575964b2f
Issue | Draft — not an issued report
Methodology version | playbook v1
Approval state of the sources (recorded, not an approval) | Approved
Draft — not an issued report
Slide 1 of 8

## Slide 2
Illustrative example — synthetic
Gate
Label | Value
Gate | G1 n/a
Phase | Diagnose n/a
Gate status | Approved n/a
Approval state (recorded, not an approval) | Approved n/a
Approver role | Executive Sponsor n/a
Submission no. | 1 n/a
Submitted at | 2026-05-21T07:00:00.000Z n/a
Submitted by | roaming.user.tl (synthetic) n/a
Draft — not an issued report
Slide 2 of 8

## Slide 3
Illustrative example — synthetic
Gate (continued)
Label | Value
Submission note | Case for Change: diagnostic, baseline, root causes and value pools (synthetic demonstration). Synthetic demonstration - approves nothing real / عرض توضيحي اصطناعي - لا يعتمد أي شيء حقيقي. n/a
Due date | n/a
Submission snapshot SHA-256 | b8382f9c0d4d54663c73eff83e1bb1956b87c1dee19f37a6f10883cb748aadd7 n/a
Decision | Approved n/a
Decided at | 2026-05-22T07:00:00.000Z n/a
Decided by | roaming.user.sp (synthetic) n/a
Rationale | Synthetic demonstration - approves nothing real / عرض توضيحي اصطناعي - لا يعتمد أي شيء حقيقي. We agree on the problem: roaming value leaks through low activation, high complaints and partner cost pressure; the attach-rate baseline is measured and the value pools are material. Proceed to Define. (Synthetic decision of 2026-05-22.) n/a
Draft — not an issued report
Slide 3 of 8

## Slide 4
Illustrative example — synthetic
Criteria
No. | Criterion | Criterion (English) | Criterion (Arabic) | Mandatory | Verified evidence | State | Missing items | Missing | Unverified evidence items | Review recommendation | Review finding
1 n/a | Diagnostic n/a | Diagnostic n/a | التشخيص n/a | Mandatory n/a | Verified evidence required n/a | Complete n/a | 0 n/a | n/a | 0 n/a | n/a | n/a
2 n/a | Baseline n/a | Baseline n/a | الخط الأساسي n/a | Mandatory n/a | Verified evidence required n/a | Complete n/a | 0 n/a | n/a | 0 n/a | n/a | n/a
3 n/a | Root causes n/a | Root causes n/a | الأسباب الجذرية n/a | Mandatory n/a | Verified evidence not required n/a | Complete n/a | 0 n/a | n/a | 0 n/a | n/a | n/a
4 n/a | Value pools n/a | Value pools n/a | مجمّعات القيمة n/a | Mandatory n/a | Verified evidence not required n/a | Complete n/a | 0 n/a | n/a | 0 n/a | n/a | n/a
5 n/a | Case for change n/a | Case for change n/a | مبررات التغيير n/a | Mandatory n/a | Verified evidence not required n/a | Complete n/a | 0 n/a | n/a | 0 n/a | n/a | n/a
Draft — not an issued report
Slide 4 of 8

## Slide 5
Illustrative example — synthetic
Criteria (continued)
No. | Criterion | Criterion (English) | Criterion (Arabic) | Mandatory | Verified evidence | State | Missing items | Missing | Unverified evidence items | Review recommendation | Review finding
6 n/a | Initial charter n/a | Initial charter n/a | الميثاق الأولي n/a | Mandatory n/a | Verified evidence not required n/a | Complete n/a | 0 n/a | n/a | 0 n/a | n/a | n/a
Draft — not an issued report
Slide 5 of 8

## Slide 6
Illustrative example — synthetic
Evidence
Gate | Kind | Supports | At submission | Review status | Content revision | SHA-256
Roaming diagnostic pack, May 2026 (synthetic) n/a | Note n/a | Diagnostic item n/a | Verified at submission n/a | Verified n/a | n/a | n/a
Draft — not an issued report
Slide 6 of 8

## Slide 7
Illustrative example — synthetic
Validation labels
Validated | The value is validated by its owner process.
Provisional | The value is provisional: pending validation or approval; it is shown and counted.
Unknown | No value is available; the cell is empty and is never shown as 0.
Stale | The value is out of date; no current number is shown.
n/a | The value does not apply to this record.
 | Totals marked as formulas are computed by the spreadsheet from the rows above; text never becomes a formula.
Draft — not an issued report
Slide 7 of 8

## Slide 8
Illustrative example — synthetic
About this file
Fonts: this presentation names IBM Plex Sans Arabic and IBM Plex Sans (SIL Open Font License 1.1) and does not embed them; a viewer without them shows a substitute font.
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.
Draft — not an issued report
Slide 8 of 8