BUSINESS
TRANSFORMATION
PLAYBOOK

A practical system to diagnose, design, mobilize, execute and realize transformation value

| 6 PHASES | 15+ READY TEMPLATES | 1 OPERATING SYSTEM |
| --- | --- | --- |

Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

Version 1.0  |  September 2026

HOW TO USE THIS PLAYBOOK

One System, Two Modes

Use this playbook in two ways: as a full end-to-end transformation methodology, or as a modular toolkit when you only need a specific deliverable (for example, a Target Operating Model, initiative business case, or benefits register).

| Mode | When to use | How |
| --- | --- | --- |
| End-to-End | New enterprise or business-unit transformation | Run Phases 1-6 sequentially. Do not launch initiatives before the North Star, outcomes and target state are clear. |
| Modular | A transformation is already underway | Enter at the relevant phase, complete the minimum mandatory templates, then reconnect to outcomes and benefits. |

Design principles

Outcome before activity: define measurable business outcomes before building a project list.

Current state before solution: diagnose economics, customer, operations, capability and technology before prescribing initiatives.

Operating model before execution: make decision rights, ownership and cross-functional ways of working explicit.

Benefits before closure: an initiative is not complete when delivered; it is complete when value is realized and sustained.

One source of truth: keep the transformation charter, roadmap, initiative portfolio and benefits register linked.

Rule of thumb Every transformation deliverable should answer one of four questions: Why change? What must become different? How will we execute? How will we prove value?

Minimum governance roles

| Role | Accountability |
| --- | --- |
| Executive Sponsor | Owns enterprise outcome, removes constraints, approves major trade-offs. |
| Transformation Lead | Integrates workstreams, drives cadence, ensures outcome realization. |
| Business Owners | Own target-state capabilities and BAU adoption. |
| Workstream Leads | Deliver initiatives and manage dependencies. |
| Finance / Value Office | Validates baseline, benefit logic, value realization. |
| Transformation Office | Governance, reporting, risks, dependencies, decisions, standards. |

METHODOLOGY

The 6-Phase Transformation System

| 1 | DIAGNOSE | Establish fact base | Current state, root causes, value pools |
| --- | --- | --- | --- |
| 2 | DEFINE | Set direction | North Star, outcomes, KPIs, guardrails |
| 3 | DESIGN | Create target state | Target Operating Model, capabilities, journeys |
| 4 | MOBILIZE | Build execution portfolio | Initiatives, business cases, roadmap, resourcing |
| 5 | TRANSFORM | Execute & govern | Operating system, workstreams, decisions, adoption |
| 6 | REALIZE | Prove & sustain value | Benefits, BAU handover, continuous improvement |

Stage gates

| Gate | Decision question | Evidence required |
| --- | --- | --- |
| G1 - Case for Change | Do we agree on the problem/opportunity and value at stake? | Diagnostic, baseline, root causes, value pools. |
| G2 - Direction | Are outcomes specific enough to steer decisions? | North Star, outcome tree, KPI definitions, guardrails. |
| G3 - Target State | Do we know what must be different operationally? | Target Operating Model, capability gaps, future journeys. |
| G4 - Mobilization | Is the portfolio executable and value-backed? | Initiative cards, business cases, roadmap, owners, capacity. |
| G5 - Scale | Are pilots/results sufficient to scale? | Performance evidence, adoption, risk closure, decision log. |
| G6 - Sustain | Is value embedded in BAU? | Benefits evidence, ownership transfer, controls, continuous improvement backlog. |

PMI/Brightline connection The playbook uses the people-centered transformation logic and transformation operating-system thinking associated with PMI/Brightline, while adding a more explicit Target Operating Model and management-consulting-style diagnostic/design layer.

PHASE 1

01  DIAGNOSE — Build the Fact Base

Objective: create a shared, evidence-based view of current performance, root causes and value at stake before solutions are chosen.

Core work

| Workstream | Key questions | Typical outputs |
| --- | --- | --- |
| Business & Financial | Where is value created/lost? Revenue, margin, cost, churn, productivity? | Baseline P&L bridge, value pools, trend analysis. |
| Customer | Where does the customer experience break? | Journey pain points, complaints, NPS/CSAT drivers. |
| Process & Operations | Where are delays, rework, bottlenecks, handoffs? | Process map, cycle time, failure demand. |
| Organization & Governance | Are roles, decision rights, incentives and accountability clear? | RACI gaps, decision latency, governance map. |
| Technology & Data | What systems/data constrain performance? | Architecture pain points, automation/data gaps. |
| Capability | What skills/capabilities are missing? | Capability heatmap, build/buy/partner needs. |

Template 1 — Current-State Diagnostic

| Dimension | Current state | Evidence / baseline | Root cause | Impact | Confidence |
| --- | --- | --- | --- | --- | --- |
| Financial | [Describe] | [Metric / source] | [Why?] | [SAR / KPI] | H / M / L |
| Customer | [Describe] | [Metric / source] | [Why?] | [KPI] | H / M / L |
| Process | [Describe] | [Metric / source] | [Why?] | [KPI] | H / M / L |
| People / Org | [Describe] | [Evidence] | [Why?] | [Impact] | H / M / L |
| Technology | [Describe] | [Evidence] | [Why?] | [Impact] | H / M / L |
| Data | [Describe] | [Evidence] | [Why?] | [Impact] | H / M / L |

Gate 1 Do not proceed with a list of projects. Proceed only when the leadership team agrees on the problem, baseline and material value pools.

TEMPLATE

Transformation Charter

| Field | Fill-in |
| --- | --- |
| Transformation name | [Name] |
| Executive sponsor | [Name / role] |
| Transformation lead | [Name / role] |
| Case for change | [What is happening and why now?] |
| North Star | [One sentence describing the future outcome] |
| In scope | [Businesses / products / journeys / geographies / capabilities] |
| Out of scope | [Explicit exclusions] |
| Baseline date | [DD/MM/YYYY] |
| Target horizon | [e.g., 18 months] |
| Top 3-5 outcomes | [Outcome + KPI + target] |
| Strategic guardrails | [Non-negotiables: regulatory, CX, capex, risk, brand, etc.] |
| Governance forum | [SteerCo / executive committee] |
| Decision rights | [What can workstreams decide vs sponsor?] |
| Success definition | [What evidence proves transformation succeeded?] |

Transformation thesis

Complete this sentence If we change [capabilities / journeys / operating model], then [customer/operational outcomes] will improve, which will create [financial/strategic benefits], because [evidence / causal logic].

Scope sanity check

Is scope tied to outcomes rather than departments?

Can each major scope item be traced to a diagnosed problem or opportunity?

Are explicit exclusions documented?

Is the baseline measurable?

Are executive decisions required to unblock the transformation visible?

PHASE 2

02  DEFINE — North Star & Outcomes

Objective: translate the case for change into measurable transformation outcomes that can steer portfolio and operating-model choices.

Outcome hierarchy

| Level | Definition | Example |
| --- | --- | --- |
| North Star | Concise description of the desired future business state. | “Make roaming effortless, trusted and economically accretive.” |
| Strategic Outcomes | What must improve for the North Star to be true. | Revenue growth, activation, customer experience, partner economics. |
| KPIs | Measures proving outcome movement. | Roaming revenue, attach rate, complaint rate, digital activation. |
| Targets | Time-bound ambition. | +X% revenue by Q4; -Y% complaints. |
| Initiative Contribution | How each initiative moves one or more outcomes. | New pass architecture → attach rate + ARPU. |

Template 2 — Outcome & KPI Tree

| Outcome | KPI | Baseline | Target | Target date | Owner | Leading indicator |
| --- | --- | --- | --- | --- | --- | --- |
| [Outcome 1] | [KPI] | [x] | [y] | [date] | [owner] | [indicator] |
| [Outcome 2] | [KPI] | [x] | [y] | [date] | [owner] | [indicator] |
| [Outcome 3] | [KPI] | [x] | [y] | [date] | [owner] | [indicator] |
| [Outcome 4] | [KPI] | [x] | [y] | [date] | [owner] | [indicator] |

Good outcome test Specific, measurable, strategically relevant, owned by a business leader, and achievable through a defined causal chain—not just “launch”, “implement” or “deliver”.

PHASE 3

03  DESIGN — Target Operating Model

Objective: define what must be different in the business—beyond projects—so the outcomes can be sustained.

The 10-dimension Target Operating Model

| Dimension | Design question |
| --- | --- |
| 1. Customer & Value Proposition | What experience/value should customers receive? |
| 2. Products & Services | What portfolio, pricing, features and service model are required? |
| 3. Journeys & Processes | What end-to-end journeys/processes must change? |
| 4. Organization | What structure, roles and accountabilities are needed? |
| 5. Governance & Decision Rights | Who decides what, at what level, using what forums? |
| 6. People & Capabilities | What skills, capacity, behaviors and incentives are required? |
| 7. Technology | What platforms, systems and integration are required? |
| 8. Data & Analytics | What data, metrics, models and ownership are needed? |
| 9. Partners & Sourcing | What should be built, bought, outsourced or partnered? |
| 10. Performance Management | How will KPIs, benefits and continuous improvement be managed? |

Template 3 — TOM Gap Matrix

| TOM dimension | Current state | Target state | Gap | Design decision | Owner |
| --- | --- | --- | --- | --- | --- |
| [Dimension] | [Today] | [Future] | [Gap] | [Decision] | [Owner] |
| [Dimension] | [Today] | [Future] | [Gap] | [Decision] | [Owner] |
| [Dimension] | [Today] | [Future] | [Gap] | [Decision] | [Owner] |
| [Dimension] | [Today] | [Future] | [Gap] | [Decision] | [Owner] |

Design principle A project portfolio is not a Target Operating Model. The TOM describes how the business will operate after the transformation; initiatives are the vehicles used to get there.

TEMPLATE

Target Operating Model Canvas

| CUSTOMER & VALUE Segments / needs / promise / experience principles [Write target-state design here] | PRODUCTS & SERVICES Portfolio / bundles / pricing / service model [Write target-state design here] |
| --- | --- |
| JOURNEYS & PROCESSES Critical E2E journeys / automation / controls [Write target-state design here] | ORGANIZATION Structure / role clarity / accountability [Write target-state design here] |
| GOVERNANCE Decision rights / forums / escalation [Write target-state design here] | PEOPLE & CAPABILITY Skills / capacity / incentives / behaviors [Write target-state design here] |
| TECHNOLOGY Platforms / architecture / integration [Write target-state design here] | DATA & ANALYTICS Sources / ownership / insight / AI / measurement [Write target-state design here] |
| PARTNERS & SOURCING Partner model / vendors / build-buy-partner [Write target-state design here] | PERFORMANCE KPIs / benefits / management cadence / CI [Write target-state design here] |

Canvas use: complete with business owners in a 90-120 minute workshop; then convert unresolved items into explicit design decisions and owners.

Template 4 — Design Decision Log

| ID | Decision required | Options | Recommendation | Decision owner | Due | Status |
| --- | --- | --- | --- | --- | --- | --- |
| D-01 | [Decision] | A / B / C | [Rec.] | [Owner] | [Date] | Open |
| D-02 | [Decision] | A / B / C | [Rec.] | [Owner] | [Date] | Open |
| D-03 | [Decision] | A / B / C | [Rec.] | [Owner] | [Date] | Open |

PHASE 4

04  MOBILIZE — Build the Transformation Portfolio

Objective: convert target-state gaps into an integrated portfolio of initiatives with clear value logic, sequencing, ownership and capacity.

From gap to initiative

Traceability chain Diagnosed issue → Target-state gap → Initiative → Deliverable → Capability change → KPI movement → Benefit.

Template 5 — Initiative Card

| Field | Fill-in |
| --- | --- |
| Initiative name | [Name] |
| Executive owner | [Name / role] |
| Workstream lead | [Name / role] |
| Problem / gap addressed | [Reference diagnostic/TOM gap] |
| Objective | [What will change?] |
| Scope | [In/out] |
| Key deliverables | [3-7 deliverables] |
| Outcome/KPI contribution | [Outcome + KPI] |
| Financial benefit | [Revenue / cost / avoided cost / capital efficiency] |
| Customer benefit | [CX / complaints / NPS / adoption] |
| Dependencies | [Teams / systems / vendors / decisions] |
| Risks | [Top risks] |
| Milestones | [Dates] |
| Required decisions | [Decision + owner + date] |

PHASE 4

Portfolio Prioritization & Roadmap

Template 6 — Prioritization Scorecard

| Initiative | Strategic fit (25%) | Financial value (25%) | Customer impact (20%) | Feasibility (15%) | Time-to-value (15%) | Weighted score |
| --- | --- | --- | --- | --- | --- | --- |
| [A] | 1-5 | 1-5 | 1-5 | 1-5 | 1-5 | [calc] |
| [B] | 1-5 | 1-5 | 1-5 | 1-5 | 1-5 | [calc] |
| [C] | 1-5 | 1-5 | 1-5 | 1-5 | 1-5 | [calc] |
| [D] | 1-5 | 1-5 | 1-5 | 1-5 | 1-5 | [calc] |

Adjust weights to the transformation context. For regulated or safety-critical transformations, risk/compliance can replace part of the weighting.

Template 7 — Wave Roadmap

| Wave | Purpose | Typical horizon | Entry criteria | Exit evidence |
| --- | --- | --- | --- | --- |
| Wave 0 — Mobilize | Baseline, governance, design decisions | 0-6 weeks | Sponsor + charter | Approved case, owners, stage gates |
| Wave 1 — Prove | Quick wins / pilots / de-risking | 1-3 months | Prioritized initiatives | Measured pilot results |
| Wave 2 — Scale | Scale validated changes | 3-9 months | Evidence + capacity | Adoption + KPI movement |
| Wave 3 — Embed | BAU integration / optimization | 6-18 months | Stable solution | Benefits sustained, ownership transferred |

Template 8 — Dependency Map

| Dependency | From | To | Type | Needed by | Owner | Status / mitigation |
| --- | --- | --- | --- | --- | --- | --- |
| [D1] | Initiative A | Initiative B | Decision / Tech / Data / Vendor | [Date] | [Owner] | [Status] |
| [D2] | Initiative C | Initiative D | [Type] | [Date] | [Owner] | [Status] |
| [D3] | External | Initiative E | [Type] | [Date] | [Owner] | [Status] |

TEMPLATE

Transformation Business Case

Use a business case at transformation level and a lighter initiative case underneath it. Finance should validate the baseline and benefit logic early—not after delivery.

| Section | Content |
| --- | --- |
| Strategic rationale | Why now; linkage to strategy; external/internal trigger. |
| Baseline | Revenue, cost, customer, operational and capability baseline. |
| Value pools | Quantified upside/downside by driver. |
| Interventions | Initiatives and target-state changes required. |
| Investment | Capex, opex, internal FTE, vendor cost, opportunity cost. |
| Benefits | Revenue uplift, cost reduction, avoidance, working capital, strategic/non-financial. |
| Timing | Benefit ramp, one-off vs recurring, implementation horizon. |
| Risks & sensitivities | Key assumptions, downside/upside cases. |
| Ownership | Benefit owner, initiative owner, Finance validator. |
| Decision ask | Funding / policy / resource / prioritization decision needed. |

Template 9 — Benefit Formula

| Benefit | Baseline driver | Change assumption | Formula | Ramp | Confidence |
| --- | --- | --- | --- | --- | --- |
| Revenue uplift | Customers × attach rate × ARPU | Attach +X pp | Δ attach × customers × ARPU | Q1-Q4 | M |
| Cost reduction | Volume × unit cost | Unit cost -X% | Volume × Δ unit cost | Q2-Q3 | H |
| [Benefit] | [Baseline] | [Assumption] | [Formula] | [Ramp] | H/M/L |

No double counting Each benefit should have a unique owner, baseline, formula and link to financial statements or an agreed non-financial KPI.

PHASE 5

05  TRANSFORM — Transformation Operating System

Objective: create a fast, disciplined mechanism for cross-functional execution, escalation, learning and decision-making while protecting outcome ownership.

Operating system layers

| Layer | Cadence | Purpose | Participants | Outputs |
| --- | --- | --- | --- | --- |
| Executive SteerCo | Monthly | Outcomes, major trade-offs, funding, escalation | Sponsor + CxOs + Transformation Lead | Decisions, unblockers, benefit view |
| Transformation Review | Bi-weekly | Portfolio health, dependencies, risks, decisions | Transformation Lead + workstream leads | Integrated status, decision log |
| Workstream Review | Weekly | Delivery, issues, actions | Workstream lead + team | Milestones, actions, RAID |
| Rapid Response / Sprint | Daily / 2-3x week | Solve high-priority cross-functional issue | Small empowered team | Test, evidence, recommendation |
| Value Review | Monthly | Validate realized benefits vs plan | Finance + benefit owners | Benefit evidence, forecast, corrective action |

Template 10 — Executive Transformation Dashboard

| Area | What to show | RAG logic |
| --- | --- | --- |
| Outcomes | Actual vs baseline vs target; trend | RAG based on target trajectory, not activity completion |
| Value | Realized / forecast benefit; investment | RAG based on validated benefit gap |
| Portfolio | Top initiatives by value/criticality | RAG by milestone + outcome risk |
| Dependencies | Top cross-functional blockers | RAG by decision date / critical path |
| Decisions | Decision needed, owner, due date, impact of delay | Red if executive decision overdue |
| People & adoption | Usage/adoption/capability signals | RAG vs adoption curve |

TEMPLATE

Governance, RACI & Decision Rights

Template 11 — Decision Rights Matrix

| Decision | Recommend | Approve | Consult | Inform | SLA |
| --- | --- | --- | --- | --- | --- |
| Business scope change | Transformation Lead | Sponsor | Business owners / Finance | Workstreams | 5 working days |
| Funding reallocation | Transformation Lead + Finance | SteerCo | Initiative owners | PMO | Next SteerCo / urgent route |
| Target-state design | Design owner | Business owner | Tech / Ops / CX / Finance | Transformation Office | 10 working days |
| Go-live / scale | Initiative owner | Business owner | Risk / Tech / CX | SteerCo | Per release plan |

Template 12 — RACI

| Deliverable | Sponsor | Transformation Lead | Business Owner | Workstream Lead | Finance | Tech/Data |
| --- | --- | --- | --- | --- | --- | --- |
| Charter | A | R | C | I | C | I |
| Target Operating Model | C | R | A | C | C | C |
| Business Case | A | R | C | C | R | C |
| Initiative Delivery | I | C | A | R | C | C |
| Benefits Validation | I | C | A | C | R | I |
| BAU Handover | I | C | A/R | R | C | C |

Governance rule Escalate decisions, not status. Every executive agenda item should state the decision required, options, recommendation, impact of delay and decision owner.

PHASE 5

People, Adoption & Change

Transformation fails when the solution is delivered but the organization does not adopt the new way of working. Manage adoption as an outcome with measurable leading indicators.

Template 13 — Stakeholder & Adoption Plan

| Stakeholder | Impact | Current stance | Required behavior | Intervention | Owner | Adoption KPI |
| --- | --- | --- | --- | --- | --- | --- |
| [Group] | H/M/L | Support / Neutral / Resist | [Behavior] | Comms / training / involvement / incentive | [Owner] | [KPI] |
| [Group] | H/M/L | [Stance] | [Behavior] | [Intervention] | [Owner] | [KPI] |
| [Group] | H/M/L | [Stance] | [Behavior] | [Intervention] | [Owner] | [KPI] |

Leading adoption indicators

Usage / activation rate

Compliance with new process

Cycle-time shift

Training completion + observed proficiency

Decision turnaround time

Percentage of transactions handled through the new journey

Exception / workaround rate

People-centered principle Involve impacted teams early in design, not only during communication. Champions are most useful when they can surface constraints and shape decisions—not simply broadcast messages.

PHASE 6

06  REALIZE — Benefits & Sustainability

Objective: convert delivered capabilities into validated business value, transfer ownership to BAU, and establish a mechanism for sustained performance.

Benefits lifecycle

| Step | Question | Output |
| --- | --- | --- |
| Identify | What benefit should this change create? | Benefit profile |
| Plan | How will it be measured, when, and by whom? | Baseline, formula, target, owner |
| Enable | What capability/deliverable must exist first? | Benefit dependency chain |
| Measure | Is the benefit appearing in actual performance? | Evidence / actuals |
| Correct | What action is needed if benefit is off track? | Recovery plan |
| Sustain | Who owns the metric after transformation closure? | BAU owner + control cadence |

Template 14 — Benefits Register

| ID | Benefit | Type | Baseline | Target | Value (SAR) | Realized | Owner | Evidence | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B01 | [Benefit] | Revenue | [x] | [y] | [SAR] | [SAR] | [Owner] | [Source] | R/A/G |
| B02 | [Benefit] | Cost | [x] | [y] | [SAR] | [SAR] | [Owner] | [Source] | R/A/G |
| B03 | [Benefit] | CX | [x] | [y] | n/a | [Actual] | [Owner] | [Source] | R/A/G |

PMI BRM connection This phase aligns with PMI Benefits Realization Management logic: identify expected benefits, deliver/measure them during execution, and sustain benefits after transition to the business.

TEMPLATE

Integrated RAID + Decision Log

Template 15 — RAID

| ID | Type | Description | Impact | Probability | Owner | Due | Mitigation / action | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Risk | [Risk] | H/M/L | H/M/L | [Owner] | [Date] | [Action] | Open |
| A01 | Assumption | [Assumption] | H/M/L | n/a | [Owner] | [Date] | [Validate] | Open |
| I01 | Issue | [Issue] | H/M/L | n/a | [Owner] | [Date] | [Resolve] | Open |
| D01 | Dependency | [Dependency] | H/M/L | n/a | [Owner] | [Date] | [Mitigate] | Open |

Template 16 — Executive Decision Log

| ID | Decision | Why now | Options | Rec. | Owner | Decision date | Impact if delayed | Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DEC-01 | [Decision] | [Trigger] | A/B/C | [Rec.] | [Exec] | [Date] | [Impact] | [Decision] |
| DEC-02 | [Decision] | [Trigger] | A/B/C | [Rec.] | [Exec] | [Date] | [Impact] | [Decision] |

Escalation principle A blocker should not remain “red” for multiple cycles without a named decision, decision owner and deadline. Convert recurring issues into explicit executive asks.

LAUNCH PLAN

First 90 Days of a New Transformation

| Window | Primary objective | Actions | Outputs |
| --- | --- | --- | --- |
| Days 0-30 | Diagnose & align | Confirm sponsor; build baseline; interview stakeholders; map journeys/processes; quantify value pools; establish initial governance. | Charter v0.9; diagnostic; baseline; issue tree; governance. |
| Days 31-60 | Define & design | Agree North Star/outcomes; build KPI tree; design TOM; run design decisions; identify initiatives; size benefits. | North Star; KPI tree; TOM; initiative backlog; initial business case. |
| Days 61-90 | Mobilize & prove | Prioritize portfolio; assign owners; sequence roadmap; launch Wave 1 pilots; establish benefits register and executive dashboard. | Roadmap; initiative cards; dashboard; benefits register; Wave 1 evidence. |

Day-90 leadership test

Can leaders explain the same case for change and North Star?

Can every initiative be traced to a target-state gap and outcome?

Are executive decision rights clear?

Is Finance aligned on baselines and benefit formulas?

Are Wave 1 initiatives producing evidence rather than only plans?

Can the transformation team show what it needs from executives this month?

WORKED EXAMPLE

Example — International Roaming Transformation

Illustrative example only. Replace assumptions with validated company data.

| Element | Illustrative content |
| --- | --- |
| Case for change | Roaming has value leakage from low adoption, fragmented propositions, inconsistent digital activation and avoidable CX friction. |
| North Star | Make international roaming effortless, trusted and economically accretive. |
| Outcomes | Revenue growth; higher attach/activation; improved partner economics; fewer complaints; higher digital self-service. |
| TOM focus | Product/pricing, digital journey, partner management, network/service assurance, data/personalization, care operations, governance. |
| Initiatives | Pass architecture redesign; digital activation; proactive travel triggers; partner-cost optimization; QoS monitoring; care simplification; analytics. |
| Governance | Monthly executive review; bi-weekly transformation review; weekly workstreams; monthly value review with Finance. |
| Benefits | Incremental roaming revenue, margin improvement, complaint reduction, digital adoption, avoided care cost. |

Illustrative traceability

| Problem | TOM gap | Initiative | KPI | Benefit |
| --- | --- | --- | --- | --- |
| Low activation | Proposition + journey | Pass redesign + digital activation | Attach rate / activation | Revenue uplift |
| High complaints | Journey + service assurance | Proactive comms + QoS monitoring | Complaint rate | CX + care cost |
| Partner cost pressure | Partner model + analytics | Partner optimization | Cost/MB, margin | Margin improvement |

REFERENCE

Transformation Health Check — 25 Questions

| ☐ 1. Is there a quantified case for change? | ☐ 2. Is the baseline trusted by Finance? |
| --- | --- |
| ☐ 3. Is there one clear North Star? | ☐ 4. Are 3-5 business outcomes measurable? |
| ☐ 5. Are outcomes owned by business leaders? | ☐ 6. Is the customer perspective explicit? |
| ☐ 7. Have root causes been separated from symptoms? | ☐ 8. Is there a defined Target Operating Model? |
| ☐ 9. Are decision rights explicit? | ☐ 10. Are capability gaps visible? |
| ☐ 11. Can every initiative be traced to a TOM gap? | ☐ 12. Can every initiative be traced to an outcome? |
| ☐ 13. Are benefits quantified without double counting? | ☐ 14. Are dependencies integrated across workstreams? |
| ☐ 15. Is sequencing based on value and feasibility? | ☐ 16. Do executive forums make decisions rather than review slides? |
| ☐ 17. Are overdue decisions visible? | ☐ 18. Are workstreams empowered within clear boundaries? |
| ☐ 19. Are adoption metrics tracked? | ☐ 20. Are frontline/business teams involved in design? |
| ☐ 21. Are benefits validated with evidence? | ☐ 22. Is BAU ownership defined before closure? |
| ☐ 23. Is a continuous-improvement backlog retained? | ☐ 24. Are lessons reused across transformations? |
| ☐ 25. Can leadership state what support the transformation needs now? | Score: ____ / 25 Top 3 actions: ____________________________ |

Interpretation

| Score | Interpretation |
| --- | --- |
| 21-25 | Strong transformation discipline; focus on value acceleration and continuous improvement. |
| 16-20 | Solid foundation; address a few structural gaps before scaling. |
| 10-15 | Execution risk is material; strengthen direction, TOM, governance or benefits. |
| 0-9 | Transformation is likely being managed as disconnected projects; reset around outcomes and operating model. |

REFERENCE

Source Base & What Is Custom

PMI / Brightline foundations

| Source | Used for |
| --- | --- |
| PMI Organizational Transformation Series | Transformation concepts, building blocks, lifecycle, readiness, implementation and orchestration. |
| Brightline Initiative / Transformation Compass | North Star, transformation operating-system thinking, people-centered transformation and transformation leadership. |
| PMI Benefits Realization Management | Benefit identification, delivery/measurement and sustainment logic. |

Custom extensions in this playbook

The 6-phase integrated methodology (Diagnose → Define → Design → Mobilize → Transform → Realize).

The 10-dimension Target Operating Model.

The stage-gate structure and most practical templates.

The initiative scoring model, governance cadence, 30-60-90 launch plan and health check.

The worked roaming example and traceability chain.

Official references

| Reference | URL |
| --- | --- |
| PMI Organizational Transformation overview | https://www.pmi.org/blog/lead-your-organization-next-transformation |
| PMI Foundations of Organizational Transformation | https://www.pmi.org/shop/india/p-/elearning/foundations-of-organizational-transformation/el164 |
| PMI Brightline | https://www.pmi.org/learning/brightline/ |
| Brightline Transformation Compass | https://www.brightline.org/resources/transformation-compass/ |
| PMI Benefits Realization Management | https://www.pmi.org/standards/benefits-realization |
| PMI BRM Framework | https://www.pmi.org/learning/thought-leadership/series/benefits-realization/benefits-realization-management-framework |

How to extend this pack The next level is to add editable Excel/PowerPoint working files: KPI tree, initiative portfolio, benefits tracker, executive dashboard and TOM workshop deck.