Mobily Transformation Hub

Illustrative example — synthetic

Transformation charter

| Product | Mobily Transformation Hub |
| --- | --- |
| Output | Transformation charter |
| Transformation | ROAMING — International Roaming Transformation |
| Subject | ROAMING — International Roaming Transformation |
| Period |  |
| As of | 2026-10-25 02:11 (Asia/Riyadh) |
| Snapshot ID | 01a1702e-e20b-75d1-8936-c66e37b1114d |
| Issue | Draft — not an issued report |
| Methodology version | playbook v1 |
| Approval state of the sources (recorded, not an approval) | Approved |

Transformation charter

| Label | Value |
| --- | --- |
| Transformation | International Roaming Transformation n/a |
| Executive sponsor | roaming.user.sp (synthetic) n/a |
| Transformation lead | roaming.user.tl (synthetic) n/a |
| Case for change | Roaming has value leakage from low adoption, fragmented propositions, inconsistent digital activation and avoidable CX friction. n/a |
| In scope | Outcomes: Revenue growth; higher attach/activation; improved partner economics; fewer complaints; higher digital self-service. Initiatives: Pass architecture redesign; digital activation; proactive travel triggers; partner-cost optimization; QoS monitoring; care simplification; analytics. n/a |
| Out of scope | Domestic tariffs and non-roaming propositions (synthetic illustrative example). n/a |
| Baseline date | 2026-06-01 n/a |
| Target horizon | 18 n/a |
| Target horizon (unit) | Months n/a |
| Governance forum | Monthly executive review; bi-weekly transformation review; weekly workstreams; monthly value review with Finance. n/a |
| Decision rights | Per the T11 decision rights matrix of this transformation (synthetic). n/a |
| Success definition | Benefits: Incremental roaming revenue, margin improvement, complaint reduction, digital adoption, avoided care cost. n/a |
| If we change (capabilities / journeys / operating model) | the roaming pass architecture, the digital activation journey and the partner model n/a |
| Then … will improve (customer / operational outcomes) | roaming attach and activation, complaint rate and partner economics n/a |
| Which will create (financial / strategic benefits) | incremental roaming revenue, avoided care cost and margin improvement n/a |
| Because (evidence / causal logic) | low activation, high complaints and partner cost pressure are the diagnosed causes of roaming value leakage (synthetic). n/a |
| G1 approval state (recorded, not an approval) | Approved n/a |

North Star

Make international roaming effortless, trusted and economically accretive.

n/a

Top outcomes

| Rank | Outcome | Status |
| --- | --- | --- |
| 1 n/a | Attach rate / activation n/a | Active n/a |
| 2 n/a | Complaint rate n/a | Active n/a |
| 3 n/a | Cost/MB, margin n/a | Active n/a |

Guardrails

| Guardrail | Category | Statement |
| --- | --- | --- |
| No bill shock (synthetic) n/a | Customer experience n/a | No roaming proposition may create an unexpected charge without an in-journey consent (synthetic). n/a |

Validation labels

| Validated | The value is validated by its owner process. |
| --- | --- |
| Provisional | The value is provisional: pending validation or approval; it is shown and counted. |
| Unknown | No value is available; the cell is empty and is never shown as 0. |
| Stale | The value is out of date; no current number is shown. |
| n/a | The value does not apply to this record. |
|  | Totals marked as formulas are computed by the spreadsheet from the rows above; text never becomes a formula. |

About this file

Fonts: this file names IBM Plex Sans Arabic and IBM Plex Sans (SIL Open Font License 1.1) and does not embed them; a viewer without them shows a substitute font.