## About
Illustrative example — synthetic
Product | Mobily Transformation Hub
Output | Wave roadmap
Transformation | ROAMING — International Roaming Transformation
Subject | ROAMING — International Roaming Transformation
Period
As of | 2026-10-25 02:11 (Asia/Riyadh)
Snapshot ID | 01a1702e-f29d-72c8-bb45-cd2cdaea57f6
Issue | Draft — not an issued report
Methodology version | playbook v1
Approval state of the sources (recorded, not an approval) | Not applicable
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Waves
Illustrative example — synthetic
Waves
Code | Name (English) | Name (Arabic) | Purpose (English) | Purpose (Arabic) | Planned start | Planned end | Owner | Status
wave_0 | Wave 0 — Mobilize | الموجة 0 — التعبئة | Baseline, governance, design decisions | الخط الأساسي، والحوكمة، وقرارات التصميم | Unknown | Unknown | Unknown | Active
wave_1 | Wave 1 — Prove | الموجة 1 — الإثبات | Quick wins / pilots / de-risking | مكاسب سريعة / تجارب / تقليل المخاطر | Unknown | Unknown | Unknown | Active
wave_2 | Wave 2 — Scale | الموجة 2 — التوسّع | Scale validated changes | توسيع التغييرات المُتحقق منها | Unknown | Unknown | Unknown | Active
wave_3 | Wave 3 — Embed | الموجة 3 — الترسيخ | BAU integration / optimization | الدمج في العمليات الاعتيادية / التحسين | Unknown | Unknown | Unknown | Active
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Initiatives
Illustrative example — synthetic
Initiatives
Code | Name | Wave | Executive owner | Workstream lead | Objective | Planned start | Planned end | Status
INI-01 | Pass redesign + digital activation | wave_1 | roaming.user.sp (synthetic) | roaming.user.wl (synthetic) | Attach rate / activation -> Revenue uplift (B0147, synthetic illustrative example). | 2026-07-03 | 2026-12-30 | Launched
INI-02 | Proactive comms + QoS monitoring | wave_1 | roaming.user.sp (synthetic) | roaming.user.wl (synthetic) | Complaint rate -> CX + care cost (B0147, synthetic illustrative example). | 2026-07-03 | 2026-12-30 | Launched
INI-03 | Partner optimization | wave_1 | roaming.user.sp (synthetic) | roaming.user.wl (synthetic) | Cost/MB, margin -> Margin improvement (B0147, synthetic illustrative example). | 2026-07-03 | 2026-12-30 | Launched
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Milestones
Illustrative example — synthetic
Milestones
Initiative | Title | Wave | Approved date | Forecast date | Actual date | Owner | Status
INI-01 | Roaming pass architecture redesigned (synthetic) | wave_1 | 2026-09-30 | 2026-09-30 | n/a | roaming.user.wl (synthetic) | Planned
INI-01 | One-tap digital activation live in the app (synthetic) | wave_1 | 2026-11-30 | 2026-11-30 | n/a | roaming.user.wl (synthetic) | Planned
INI-02 | QoS monitoring live for the top roaming destinations (synthetic) | wave_1 | 2026-10-15 | 2026-10-15 | n/a | roaming.user.wl (synthetic) | Planned
INI-02 | Proactive travel notifications live (synthetic) | wave_1 | 2026-12-15 | 2026-12-15 | n/a | roaming.user.wl (synthetic) | Planned
INI-03 | Partner cost analytics baseline delivered (synthetic) | wave_1 | 2026-09-15 | 2026-09-15 | n/a | roaming.user.wl (synthetic) | Planned
INI-03 | Partner usage feed live for digital activation (synthetic) | wave_1 | 2026-09-28 | 2026-09-28 | n/a | roaming.user.wl (synthetic) | Planned
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Dependencies
Illustrative example — synthetic
Dependencies
Code | From initiative | To initiative | Type | Description | Needed by | Owner | Status
DEP-01 | INI-03 | INI-01 | Data | Digital activation needs the partner usage feed from Partner optimization (synthetic). | 2026-10-01 | roaming.user.wl (synthetic) | Open
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.

## Legend
Illustrative example — synthetic
Validation labels
Validated | The value is validated by its owner process.
Provisional | The value is provisional: pending validation or approval; it is shown and counted.
Unknown | No value is available; the cell is empty and is never shown as 0.
Stale | The value is out of date; no current number is shown.
n/a | The value does not apply to this record.
Totals marked as formulas are computed by the spreadsheet from the rows above; text never becomes a formula.
Practical synthesis inspired by PMI Organizational Transformation, Brightline Transformation Compass and PMI Benefits Realization Management; extended with a custom Target Operating Model toolkit.